## Phase 1 Deployment
Item # | Prerequisites | PreDeployment | Who? | What?
DRTRNP
1a | none | Create & compile new schema objects | DBA | new tables
1b | none | Create & compile new schema objects | DBA | new synonyms
1c | none | Create & compile new schema objects | DBA | new views
1d | none | Create & compile new schema objects | DBA | new functions
1e | none | Add space to database | DBA
2 | none | Add new tables to Truncate Tables | Pam
3 | none | Turnover new SQL files to UNIX | Nancy
4 | 3 | Create & run Initial load jobs and process flows in Applications Manager | Pam
5 | 1a | Deploy Informatica mappings & run load | Support Team?
6 | 1a, 1d, 1e, 3, 4 | Initial Load of all "R12_" source tables | Pam
7 | 6 | Analyze all newly loaded tables | Pam?
8 | do step 1 first | Alter existing tables - Add columns & indexes | DBA
9 | 8 | One time update of new columns for history data | Pam
DWTRNP
10a | none | Create & compile new schema objects | DBA | new tables
10b | none | Create & compile new schema objects | DBA | new synonyms
10c | none | Create & compile new schema objects | DBA | new views
10d | none | Create & compile new schema objects | DBA | new functions
10e | none | Add space to database | DBA
11 | none | Add new tables to Truncate Tables | Pam
12 | none | Turnover new SQL files to UNIX | Nancy
13 | 12 | Create & run jobs and process flows in Appworx? | Pam
No Informatica mappings
14 | 10a, 10d, 10e, 12, 13 | Initial Load of all "R12_" source tables | Pam
15 | 14 | Analyze all newly loaded tables | Pam?
16 | do step 10 first | Alter existing tables - Add indexes | DBA
|  | ACTUATE SERVER CHANGES | Innovent
GO LIVE!
DRTRNP
L1a | go live date | Backup Tables in List | DBA
L2a | 1 thru 16 & L1a | Compile MVW changes | DBA
DWTRNP
L1b | go live date | Backup Tables in List | DBA
L2b | 1 thru 16 & L1b | Alter existing tables - Add columns & indexes | DBA
L3 | L1b & L2b | One time update of new columns for history data | DBA & Pam
L4 | 1 thru 16, L2a, L2b, L3 | Compile Packages | DBA
L5 | L2a | Run DRTRNP MVWs | Pam
L6 | L4 & L5 | Run DWTRNP Packages | Pam
ACTUATE
L7 | L6 | Run IOBs | Innovent
L8 | L5, L6, L7 | Run Reports | Innovent
L9 |  | Create & schedule Monthly load jobs for DRTRNP & DWTRNP in App Man, Appworx, Informatica | Pam
L10 |  | Schedule IOBs? | Innovent
L11 |  | Schedule reports? | Innovent